## Project Charter
IT GRC Risk & Compliance Assessment
Organization | Northstar Financial Services
Project | IT GRC Risk & Compliance Assessment
Assessment Type | Cybersecurity Risk & Control Assessment
Framework | NIST CSF / NIST SP 800-53
Analyst | Mia L. Pearson
Assessment Date | 2026-10-05
Business Overview | Northstar Financial Services is a fictional 150-employee financial services organization that uses Microsoft 365, AWS, SaaS applications, and a customer-facing web portal to process and store sensitive customer information.
Assessment Objectives:Identify cybersecurity risks Evaluate existing security controls Assess control effectiveness Identify control gaps Prioritize remediation activities Develop an executive-level GRC dashboard
Scope:AWS production environment Microsoft 365 Employee endpoints Customer portal Identity and access management Vulnerability management Incident response Third-party risk

## Asset Inventory
Asset-ID | Asset | Owner | Type | Criticality | Data
AST-001 | AWS Production | IT Manager | Cloud | Critical | Customer PII
AST-002 | Microsoft 365 | IT Manager | SaaS | High | Employee/Customer Data
AST-003 | Customer Portal | Engineering | Application | Critical | Customer PII
AST-004 | Employee Laptops | IT | Endpoint | High | Company Data
AST-005 | HR Systems | HR | SaaS | High | Employee PII
AST-006 | CRM Platform | Sales Manager | SaaS | High | Customer Data
AST-007 | Backup Enviroment | IT Manager | Infrastructure | Critical | Customer Data
AST-008 | Corporate Network | IT Manager | Network | High | Company Data

## Risk Scoring
Likelihood Scoring |  |  | Impact Scoring |  | Risk Rating
Score | Definition |  | Score | Definition | Score Range | Rating
1 | Rare |  | 1 | Minimal | 2026-01-04 | Low
2 | Unlikely |  | 2 | Minor | 2026-05-09 | Medium
3 | Possible |  | 3 | Moderate | 2026-10-16 | High
4 | Likely |  | 4 | Major | 17-25 | Critical
5 | Almost Certain |  | 5 | Severe
Risk Calculation
Risk Score | Likelihood × Impact
Example | Likelihood 4 × Impact 5 = Risk Score 20
Risk Rating Formula |  | 1–4 = Low
5–9 = Medium
10–16 = High
17–25 = Critical

## Risk Register
Risk ID | Asset | Risk Description | Threat | Vulnerability | Likelihood | Impact | Risk Score | Risk Rating | Owner | Treatment | Status
R-001 | AWS Production | Unauthorized access to production environment | Compromised credentials | MFA not enforced for all privileged accounts | 4 | 5 | 20 | Critical | IT Manager | Mitigate | Open
R-002 | Microsoft 365 | Unauthorized access to employee accounts | Credential theft | Inconsistent MFA enforcement | 4 | 4 | 16 | High | IT Manager | Mitigate | Open
R-003 | Employee Laptops | Malware Infection | Phishing | Inconsistent endpoint protection | 4 | 4 | 16 | High | IT Manager | Mitigate | Open
R-004 | AWS Production | Exploitation of unpatched vulnerabilities | External attacker | Delayed patching | 4 | 5 | 20 | Critical | IT Manager | Mitigate | Open
R-005 | Customer Portal | Customer Data Breach | Web Attacker | Application security weakness | 3 | 5 | 15 | High | Engineering Manager | Mitigate | Open
R-006 | Microsoft 365 | Former employee retains access | Insider/External attacker | Inconsistent account termination process | 3 | 5 | 15 | High | IT Manager | Mitigate | Open
R-007 | Backup Environment | Inability to recover after ransomware | Ransomware | Backup recovery procedures not tested | 3 | 5 | 15 | High | IT Manager | Mitigate | Open
R-008 | CRM Platform | Third-party vendor exposes customer information | Vendor compromise | Limited vendor security assessment | 3 | 4 | 12 | High | GRC Manager | Mitigate | Open
R-009 | Corporate Network | Unauthorized network access | External attacker | Network segmentation gaps | 3 | 4 | 12 | High | IT Manager | Mitigate | Open
R-010 | Customer Portal | Security incident is not detected quickly | Cyber attacker | Insufficient centralized logging | 3 | 5 | 15 | High | Security Manager | Mitigate | Open

## Evidence Tracker
Evidence ID | Control ID | Evidence Requested | Owner Status | Review | Result | Notes
EV-001 | AC-01 | MFA configuration report | IT | Received | Satisfactory | Configuration report received; verify all privileged accounts are enrolled.
EV-002 | AC-02 | Quarterly user access review | IT | Missing |  | No evidence provided.
EV-003 | VM-01 | Vulnerability scan report | Security | Received | Partial | Review critical vulnerabilities and remediation dates.
EV-004 | IR-01 | Incident Response Plan | Security | Missing |  | Plan not provided for review.
EV-005 | IR-02 | Incident response tabletop documentation | Security | Missing |  | No exercise documentation provided.
EV-006 | DP-01 | Encryption-at-rest configuration report | IT | Received | Satisfactory | Verify encryption settings for sensitive data.
EV-007 | TP-01 | Vendor security assessment | GRC | Partial | Partial | Confirm assessments exist for all critical vendors.
EV-008 | SA-01 | Security awareness completion report | HR | Received | Satisfactory | Verify annual training completion.
EV-009 | AC-03 | Employee termination checklist | HR/IT | Partial | Partial | Check whether account deactivation was timely and documented.

## Control Assessment
NORTHSTAR FINANCIAL SERVICES ¦ GRC ASSESSMENT
Control Assessment & Validation
Control ID | Control Requirement | Evidence Reviewed | Design Effectiveness | Operating Effectiveness | Assessment Finding | Finding Severity | Assessment Status
AC-01 | MFA is required for all privileged accounts. | MFA configuration report | Effective | Partially Effective | Two legacy privileged accounts are not enrolled in MFA | Critical | Finding
AC-02 | Usesr access is reviewed quartery | No evidence provided | Ineffective | Ineffective | No formal quarterly user access review process has been established | High | Finding
VM-01 | Critical vulnerabilities are remediated within 30 days | Vulnerability scan report | Effective | Partially Effective | Several critical vulnerabilities exceeded the 30-day remediation target | High | Finding
IR-01 | A documented Incident Response Plan is maintained | Incident Response Plan not provided | Ineffective | Ineffective | An Incident Response Plan has not been formally documented and approved | High | Finding
IR-02 | Incident response tabletop exercises are conducted annually | No tabletop exercise documentation provided | Ineffective | Ineffective | No significant control gaps identified in the sample assessment | Low | No Finding
DP-01 | Sensitive information is encrypted at rest | Encryption-at-rest configuration report | Effective | Effective | No significant control gaps identified in the sample assessment | Low | No Finding
DP-02 | Sensitive information is encrypted in transit | TLS configuration report | Effective | Effective | No significant control gaps identified in the sample assessment | Low | No Finding
TP-01 | Critical third-party vendors undergo security assessments | Vendor security assessment | Effective | Partially Effective | Security assessments are not consistently documented for all critical vendors | Medium | Finding
SA-01 | Employees complete annual security awareness training | Security awareness completion report | Effective | Effective | No significant control gaps identified in the sample assessment | Low | No Finding
AC-03 | Terminated employee accounts are disbaled promptly | Employee termination checklist | Effective | Partially Effective | Account termination procedures exist, but documentation was inconsistent for several terminated employees | High | Finding

## Gap Assessment
NORTHSTAR FINANCIAL SERVICES ¦ GRC ASSESSMENT
Gap Assessment & Remediation Priorities
Gap ID | Control ID | Identified Gap | Current State | Expected State | Business Impact | Severity | Recommended Action | Owner | Status
GAP-001 | AC-01 | Two legacy privileged accounts are not enrolled in MFA. | MFA is enabled for most privileged accounts, but two legacy accounts are excluded. | All privileged accounts require MFA. | Unauthorized access could expose sensitive systems and data. | Critical | Enroll the two legacy accounts in MFA or document an approved alternative control. | IT | In Progress
GAP-002 | AC-02 | No formal quarterly user access review process has been established. | No documented quarterly access review evidence was provided. | User access is reviewed and documented quarterly. | Excessive or inappropriate access could remain undetected. | High | Establish quarterly access reviews, assign reviewers, and retain approvals. | IT | Open
GAP-003 | VM-01 | Several critical vulnerabilities exceeded the 30-day remediation target. | Critical vulnerability remediation is not consistently completed within 30 days. | Critical vulnerabilities meet the 30-day target or have approved exceptions. | Unpatched systems may be exploited, causing disruption or data exposure. | High | Prioritize overdue vulnerabilities and track remediation dates and exceptions. | Security | Open
GAP-004 | IR-01 | An Incident Response Plan has not been formally documented and approved. | A formally approved plan was not provided. | A documented, approved, maintained Incident Response Plan exists. | Response may be delayed or inconsistent during a security incident. | High | Document the plan, obtain approval, and assign review ownership. | Security | Open
GAP-005 | IR-02 | No evidence of an annual incident response tabletop exercise was provided. | Exercise completion could not be verified. | Annual tabletop exercises are conducted and documented. | Teams may be unprepared to coordinate during an incident. | High | Schedule an exercise and retain attendance, results, and improvement actions. | Security | Open
GAP-006 | TP-01 | Security assessments are not consistently documented for all critical vendors. | Assessment records are incomplete for some critical vendors. | Critical vendors undergo documented security assessments periodically. | Third-party security weaknesses may go unidentified. | Medium | Complete outstanding vendor assessments and track periodic reassessments. | GRC | Open
GAP-007 | AC-03 | Account termination documentation was inconsistent for several terminated employees. | Procedures exist, but timely deactivation evidence is inconsistent. | Terminated employee accounts are disabled promptly and documented. | Former employees could retain access longer than intended. | High | Standardize termination evidence and periodically test deactivation timeliness. | HR/IT | Open

## Remediation Plan
NORTHSTAR FINANCIAL SERVICES ¦ GRC ASSESSMENT
Remediation Plan & Action Tracking
Action ID | Gap ID | Control ID | Remediation Action | Priority | Owner | Start Date | Target Date | Success Criteria | Status | Dependencies / Notes
RA-001 | GAP-001 | AC-01 | Enroll both legacy privileged accounts in MFA; document any approved exception and compensating control. | Critical | IT | 2026-10-19 | 2026-11-02 | All privileged accounts are enrolled in MFA or have a formally approved exception. | In Progress | Confirm account inventory and application compatibility.
RA-002 | GAP-002 | AC-02 | Define quarterly access review procedure, assign reviewers, record approvals, and retain evidence. | High | IT | 2026-10-19 | 2026-11-18 | A documented review is completed and evidence is retained for all in-scope systems. | Not Started | Coordinate system owners and HR for role/termination data.
RA-003 | GAP-003 | VM-01 | Prioritize overdue critical vulnerabilities, assign remediation owners, and track due dates and approved exceptions. | High | Security | 2026-10-19 | 2026-11-18 | All critical vulnerabilities meet the 30-day target or have approved, tracked exceptions. | In Progress | Validate scan results and production change windows.
RA-004 | GAP-004 | IR-01 | Draft an Incident Response Plan covering roles, escalation, communications, containment, recovery, and lessons learned. | High | Security | 2026-10-19 | 2026-11-18 | Plan is approved by management, assigned an owner, and stored in an accessible repository. | Not Started | Consult IT, Legal, Privacy, and business leadership.
RA-005 | GAP-005 | IR-02 | Schedule and conduct an incident-response tabletop exercise; record attendees, outcomes, and improvement actions. | High | Security | 2026-10-19 | 2026-12-18 | Exercise completed and records plus tracked follow-up actions are retained. | Not Started | Exercise can be scheduled after the incident response plan is approved.
RA-006 | GAP-006 | TP-01 | Inventory critical vendors, complete outstanding security assessments, and establish a periodic reassessment schedule. | Medium | GRC | 2026-10-19 | 2026-12-03 | All critical vendors have current, documented assessments or approved risk exceptions. | Not Started | Confirm criticality tier and vendor owners.
RA-007 | GAP-007 | AC-03 | Standardize HR/IT termination checklist and retain timestamped evidence of account disablement for each termination. | High | HR/IT | 2026-10-19 | 2026-11-18 | Sampled terminations show timely deactivation with complete supporting evidence. | Not Started | Align HR notification and IT account disablement workflows.

## POA&M
NORTHSTAR FINANCIAL SERVICES ¦ GRC ASSESSMENT
Plan of Action and Milestones (POA&M)
POA&M ID | Gap ID | Action ID | Weakness / Finding | Milestone | Milestone Owner | Planned Completion | Actual Completion | Status | Completion Evidence | Residual Risk / Notes
POAM-001 | GAP-001 | RA-001 | Two legacy privileged accounts are not enrolled in MFA. | Identify the two legacy accounts and confirm application compatibility. | IT | 2026-10-22 |  | In Progress | Pending: account inventory and compatibility review. | Critical until MFA enrollment or an approved compensating control is verified.
POAM-001 | GAP-001 | RA-001 | Two legacy privileged accounts are not enrolled in MFA. | Enroll accounts in MFA or obtain formally approved exception. | IT | 2026-11-02 |  | Not Started | Pending: MFA configuration evidence and approval record. | Reassess after evidence is reviewed.
POAM-002 | GAP-002 | RA-002 | No formal quarterly user access review process has been established. | Draft access review procedure and define in-scope systems. | IT | 2026-10-29 |  | Not Started | Pending: approved procedure. | High until recurring reviews are completed and evidenced.
POAM-002 | GAP-002 | RA-002 | No formal quarterly user access review process has been established. | Complete first review, record approvals, and retain evidence. | IT | 2026-11-18 |  | Not Started | Pending: completed access review and approval records. | Validate that exceptions have owners and due dates.
POAM-003 | GAP-003 | RA-003 | Several critical vulnerabilities exceeded the 30-day remediation target. | Validate overdue critical findings and assign remediation owners. | Security | 2026-10-24 |  | In Progress | Pending: current scan and assigned remediation tickets. | High until remediation or approved exception is confirmed.
POAM-003 | GAP-003 | RA-003 | Several critical vulnerabilities exceeded the 30-day remediation target. | Remediate or document approved exceptions for overdue critical findings. | Security | 2026-11-18 |  | Not Started | Pending: rescans, change records, or approved exceptions. | Re-scan to verify remediation.
POAM-004 | GAP-004 | RA-004 | An Incident Response Plan has not been formally documented and approved. | Draft plan covering roles, escalation, communications, containment, and recovery. | Security | 2026-11-08 |  | Not Started | Pending: draft plan. | High until the plan is approved and accessible.
POAM-004 | GAP-004 | RA-004 | An Incident Response Plan has not been formally documented and approved. | Obtain management approval and publish the controlled plan. | Security | 2026-11-18 |  | Not Started | Pending: approval and publication record. | Confirm plan owner and review cadence.
POAM-005 | GAP-005 | RA-005 | No evidence of an annual incident response tabletop exercise was provided. | Define scenario, participants, objectives, and schedule. | Security | 2026-11-28 |  | Not Started | Pending: exercise plan and invitations. | High until exercise completion and lessons learned are documented.
POAM-005 | GAP-005 | RA-005 | No evidence of an annual incident response tabletop exercise was provided. | Conduct exercise and track lessons learned to closure. | Security | 2026-12-18 |  | Not Started | Pending: attendance, exercise notes, and improvement actions. | Exercise should test the approved incident response plan.
POAM-006 | GAP-006 | RA-006 | Security assessments are not consistently documented for all critical vendors. | Confirm critical vendor inventory, tiering, and assessment status. | GRC | 2026-11-03 |  | Not Started | Pending: critical vendor inventory. | Medium until assessment coverage is verified.
POAM-006 | GAP-006 | RA-006 | Security assessments are not consistently documented for all critical vendors. | Complete missing assessments or record approved risk exceptions. | GRC | 2026-12-03 |  | Not Started | Pending: assessment reports or exception approvals. | Set reassessment dates for critical vendors.
POAM-007 | GAP-007 | RA-007 | Account termination documentation was inconsistent for several terminated employees. | Standardize HR/IT termination checklist and required timestamps. | HR/IT | 2026-10-29 |  | Not Started | Pending: approved checklist and process documentation. | High until timely deactivation is supported by evidence.
POAM-007 | GAP-007 | RA-007 | Account termination documentation was inconsistent for several terminated employees. | Sample completed terminations and verify timely deactivation evidence. | HR/IT | 2026-11-18 |  | Not Started | Pending: sample test results and deactivation logs. | Document exceptions and corrective actions.

## Vendor Risk
Vendor | Service | Data Access | SOC 2 | MFA | Encryption | Incident Response | Risk Rating | Vendor | Assessment rationale
CloudHost AWS Services | Cloud Hosting | High | Yes | Yes | Yes | Yes | Low | CloudHost AWS Services | Low provisional control risk based on simulated positive responses; review SOC 2 and cloud shared responsibility.
PayFlow HR | Payroll Processing | High | Yes | Yes | Yes | Yes | Medium | PayFlow HR | Medium exposure due to sensitive employee/payroll data despite positive simulated responses.
CustomerCRM | Customer Relationship Management | High | No | Partial | Yes | Partial | High | CustomerCRM | High provisional risk: no SOC 2 evidence, partial MFA and incident response, and customer data exposure.
ASSESSMENT NOTES
Scenario | Fictional vendor questionnaire responses for the North Star Financial Services portfolio assessment
Important | SOC 2 and other Yes/No/Partial entries represent simulated responses, not verified supporting evidence.
Interpretation | Risk ratings are illustrative and should be validated using business criticality, evidence review, and compensating controls.
Vendor risk summary | Count
Low | 1
Medium | 1
High | 1

## Dashboard
NORTH STAR FINANCIAL SERVICES ¦ GRC DASHBOARD
Executive risk overview • Linked to your existing portfolio tabs
TOTAL RISKS |  | CRITICAL RISKS |  | HIGH RISKS | OPEN FINDINGS
10 |  | 2 |  | 8 | 7
RISK DISTRIBUTION | COUNT |  | CONTROL EFFECTIVENESS | COUNT | REMEDIATION STATUS | COUNT
Critical | 2 |  | Effective | 3 | Not Started | 5
High | 8 |  | Partially Effective | 4 | In Progress | 2
Medium | 0 |  | Ineffective | 3 | Completed | 0
Low | 0 |  | Not Implemented | 0 | Delayed | 0
Total Risk | 10 |  | Not Assessed | 0
|  |  | Total Assessed | 10
HOW TO USE THIS DASHBOARD
1. In your existing Google Sheets project, go to File > Import > Upload and select this file.
2. Choose Insert new sheet(s). Confirm the imported tab is named exactly Dashboard.
3. The formulas expect these tab names: Risk Register, Control Assessment, and Remediation Plan.
4. Risk Register ratings must be in column I; Control Assessment operating effectiveness in column E.
5. Remediation Plan statuses must be in column G (Open / In Progress / Completed / Delayed).
6. All numbers update when you change the records on those tabs.
NOTE: This file contains only the Dashboard. Before importing, formulas may display errors because source tabs are in your existing workbook.